## SPRINT 1 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 1 BACKLOG | [7 empty] | Completed | High
SPRINT 1 - ENVIRONMENT SETUP | [5 empty] | % COMPLETED | 100% | In Progress | Low
On Hold
TASK | Issue #1 | As the Administrator of a Career Services Application, I would like to use GitHub to carry out the Project Management Activities of a Scrum Team to track the project workflow
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
2 | Setup GitHub Repository | Sadath Roshan | - | 2023-07-07 | 100% | Completed | High
3 | Read Documentation on GitHub Projects and watch YouTube videos on setting up Project Board | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Medium
4 | Template the Project Board as a Scrum Project | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Medium
5 | Automate Project Workflows for easier management | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Low
TASK | Issue #32 | Complete the Documentation for the SPRINT 1 Deliverables
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
7 | Document and Update the Minutes of the Product Meeting and the Sprint Planning Meeting | Manasa Yalakala | - | 2023-10-07 | 100% | Completed | High
8 | Update README.md for SPRINT 1 | Lakshya Kalia | - | 2023-10-07 | 100% | Completed | Medium

## SPRINT 2 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 2 BACKLOG | [7 empty] | Completed | High
SPRINT 2 - EPIC 1- EMPLOYER MANAGEMENT AND JOB POSTING | [5 empty] | % COMPLETED | 94.7% | In Progress | Low
On Hold
TASK | Issue #13 | As an Employer, I want to be able to create an account on the career services application, so that I can complete the registration process successfully
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
17 | Create wireframe for the registration screen for employer | Lakshya Kalia | 2 | 14/07/2023 | 100% | Completed | High
21 | Create the registration screen for employer and candidate roles in the frontend | Lakshya Kalia, Sindoora Rao | 5 | 14/07/2023 | 100% | Completed | Medium
52 | Perform Hashing to store the user password for authentication | Pankaj Deep, Sadath Roshan | 8 | 17/07/2023 | 100% | Completed | High
24 | Create the functionality for sending data to backend for registration | Lakshya Kalia, Sindoora Rao, Pankaj Deep, Manasa Yalakala | 5 | 14/07/2023 | 100% | Completed | Medium
53 | Setup the SQL Database and create a table to store the information on - Employers | Pankaj Deep, Sadath Roshan | 8 | 16/07/2023 | 100% | Completed | High
22 | Create a POST API to add employers information to the system database. | Manish Gautam, Pankaj Deep, Manasa Yalakala | 5 | 16/07/2023 | 100% | Completed | Low
TASK | Issue #20 | As an Employer, I want to log into my account using my Email and Password, so that I can access the platforms to post jobs and hire candidates
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
38 | Create wireframe for Login Screen of Employer | Lakshya Kalia, Sindoora Rao | 3 | 16/07/2023 | 100% | Completed | High
39 | Design the Login screen of the Employer | Lakshya Kalia, Sindoora Rao | 5 | 16/07/2023 | 100% | Completed | High
54 | Create the functionality for sending data to backend for login for employer | Manish Gautam, Pankaj Deep, Manasa Yalakala | 5 | 16/07/2023 | 100% | Completed | Medium
44 | Perform User Authentication, by mapping the login password to the hashed password | Pankaj Deep, Sadath Roshan, Manasa Yalakala | 8 | 17/07/2023 | 100% | Completed | Medium
56 | Display Employer dashboard on login | Team | 8 | 16/07/2023 | 100% | Completed | Medium
TASK |  | As an Employer, I would like to be able to Update my account information/profile by updating new milestones, or just to keep the profile up-to-date.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #27 | As an employer, I want to post job opportunities on the Career Services Application. I would like to post the information on Company Name, Job title, Project/Team name, Job location, Type of work, Expected Start date, Estimated Pay Scale, Job Description, and the Required Skills for the role. So that I can enable candidates to better understand the opportunity they are pursuing.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
62 | Create wireframe for forms to enter employer information into the application. | Lakshya Kalia, Manasa Yalakala | 3 | 16/07/2023 | 100% | Completed | Medium
63 | Create wireframe for the Employer Dashboard along with a button to create a new Job Posting. | Lakshya Kalia, Sindoora Rao | 5 | 16/07/2023 | 100% | Completed | Medium
64 | Create confirmation box to display "Job has been posted" once the Employer has successfully submitted the form | Lakshya Kalia, Sindoora Rao | 2 | 16/07/2023 | 100% | Completed | Medium
65 | Create new database table for the Job details to store the Job Posting information with a Job ID | Sadath Roshan, Pankaj Deep | 8 | 16/07/2023 | 100% | Completed | High
66 | Create POST API to create a record of the new jobs in the Jobs tables of the database | Manish Gautham, Pankaj deep | 5 | 17/07/2023 | 100% | Completed | Medium
TASK | Issue #47 | As an Employer, I want to view all of my job postings from my personal dashboard so that I can review each of the posts and make changes if necessary.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
67 | Design UI for the Job Cards with the relevant information | Lakshya Kalia | 5 | 17/07/2023 | 100% | Completed | Medium
68 | Update the Dashboard wireframe with each Job Posting as a card, with Job Title, Job Location, Start Date and a short version of the Job Description is displayed. | Sindoora Rao, Sadath Roshan | 8 | 17/07/2023 | 100% | Completed | Medium
69 | Create a GET API to retrieve all the jobs posted by the Employer using the Employer ID as key from the Jobs table | Manish Gautham, Pankaj deep | 5 | 18/07/2023 | 100% | Completed | High
TASK | Issue #48 | As an Employer, I want to view individual Job posting and access the list of Candidates who have applied for the position, so that I can review their profile to identify a suitable hire for the role
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
70 | Create Wireframe for Job Post page. It should contain the details of the Job Posting, along with a list of all the candidates who have applied for the role. | Lakshya Kalia, Sindoora Rao | 8 | 17/07/2023 | 100% | Completed | Medium
71 | Create the back-end functionality to interface with the database. | Manish Gautham, Manasa Yalakala | 5 | 17/07/2023 | 100% | Completed | Medium
72 | Create GET API to retrieve all the Information of the Job Posting using the Job ID as key | Sadath Roshan, Pankaj deep Sahota | 5 | 17/07/2023 | 100% | Completed | High
73 | Create GET API to retrieve the list of candidates who have applied for the job, using the Candidate ID as key on the Jobs Table | Pankaj Deep, Sadath Roshan, Manish Gautham | 5 | 18/07/2023 | 100% | Completed | High
TASK | Issue #49 | As an Employer, I want to access each of the applicant's profile page, and also be able to download their Resume's, to help me better review the application, comparing their skills to the job requirments to find the perfect candidate for the postion.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
74 | Create each of the candidate names as a clickable field to access the Candidate Profile Page. | Sindoora Rao, Sadath Roshan | 5 | 17/07/2023 | 100% | Completed | Medium
75 | Create a wireframe for the Candidate's Profile Page, containing all the information of the candidate, along with their resume | Lakshya Kalia, Manasa Yalakala | 5 | 18/07/2023 | 100% | Completed | Medium
76 | Create a GET API to retrieve all the Information of the Candidate from their profile, to display to the Employer | Manish Gautham, Pankaj deep | 8 | 18/07/2023 | 100% | Completed | Medium
77 | Create functionality to allow the Employer to download the Candidate's Resume or view it on a separate browser webpage. | Pankaj Deep, Sadath Roshan, Lakshya Kalia | 21 | 18/07/2023 | 25% | In Progress | High
TASK | Issue #50 | As an Employer, I want the provision to select eligible candidates to move further to the next step of the hiring process or to reject an application that does not meet the requirements.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
78 | Update the Candidate Profile wireframe to add two buttons "Select Candidate for Next Round" or "Decline Application" | Sindoora Rao | 8 | 17/07/2023 | 100% | Completed | Medium
79 | Update the Candidate list section of the Job Post Wireframe to highlight the selected candidates in "Green" and provide a button to "Decline Selection" | Lakshya Kalia, Sindoora Rao, Sadath Roshan | 8 | 18/07/2023 | 100% | Completed | Medium
80 | Redirect Employer to the Candidate List once a decision has been made on a Candidate's profile | Sindoora Rao, Manasa Yalakala | 5 | 18/07/2023 | 100% | Completed | Medium
TASK | Issue #51 | As an Employer, I want to be able to shortlist candidates, and find the updated list of candidates, so that I can contact them individually to schedule the next steps of the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
81 | Update the Job Posting Wireframe to add a button at the end of the list to "Shortlist Candidates", which updates the new list to the remaining candidates. | Lakshya Kalia, Sindoora Rao, Manasa Yalakala | 13 | 17/07/2023 | 0% | In Progress | Medium
82 | Create a PUT API to update the status of the Candidate's Application in the Jobs table | Manish Gautham, Pankaj deep | 8 | 18/07/2023 | 100% | Completed | Medium
83 | Create GET API to display a new list of Shortlisted Candidates, with Job ID as key and the application status as short-listed from the Jobs table | Sadath Roshan, Pankaj Deep | 8 | 18/07/2023 | 100% | Completed | Medium
SPRINT 2 - EPIC 2 - CANDIDATE PROFILE MANAGEMENT AND JOB APPLICATION | [5 empty] | % COMPLETED | 74.19%
TASK | Issue #14 | As a Candidate, I want to be able to register on the career services application, so that I can register myself to browse available jobs
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
34 | Create a wireframe for Registration screen of Candidate | Lakshya Kalia, Sindoora Rao | 5 | 16/07/2023 | 100% | Completed | Medium
41 | Create a functionality in the backend for registering the Candidate | Lakshya Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
57 | Create a table in the Database to store the Login Information of the Candidates | Manish Gautham, Pankaj deep | 13 | 16/07/2023 | 100% | Completed | High
58 | Create a POST API to register a new Candidate in the database | Manish Gautham, Manasa Yalakala | 8 | 16/07/2023 | 100% | Completed | High
TASK | Issue #18 | As a Candidate, I want to log into my account using my Email and Password, so that I can, access the platform's features specific to job seekers.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
37 | Design a wireframe for the Login page | Lakshya Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
59 | Create a GET API to verify the login credentials of the Candidate | Manish Gautham, Pankaj deep | 8 | 16/07/2023 | 100% | Completed | Medium
60 | Set-up password hashing to ensure that the Candidate's credentials are safely stored and retrieved | Pankaj deep, Sadath Roshan | 13 | 16/07/2023 | 100% | Completed | Medium
61 | Display Candidate Dashboard on Login | Manish Gautham, Manasa Yalakala | 5 | 17/07/2023 | 100% | Completed | High
TASK | Issue #31 | As a Candidate, I want to create/customize my own profile. I want to be able to provide my Name, Email address, Educational qualifications, Prior work experience (if any), Licences and Certifications, and any relevant skills, I also want to be able to Upload my own resume, so that I can apply to job postings.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
84 | Design a wireframe for the Candidate Profile | Lakshya Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
85 | Create UI for the Candidate to enter their Personal Information and update their Professional Experience | Sindoora Rao, Sadath Roshan | 21 | 16/07/2023 | -% | On Hold | High
86 | Provide option to Upload a file (Resume) in a .pdf or a .docx format on to the profile | Pankaj deep, Sadath Roshan | 13 | 17/07/2023 | -% | On Hold | Medium
87 | Create new table in the Database to register the Candidate Profile | Sadath Roshan, Pankaj Deep, Manish Gautham | 8 | 17/07/2023 | 100% | Completed | Medium
88 | Create a POST API to store the Candidate Profile information using the CandidateID as key | Manish Gautham, Manasa Yalakala | 8 | 18/07/2023 | -% | On Hold | High
89 | Create a PUT API to update the Link with the location to the Uploaded Resume file on the Candidate Profile using the candidateID as key | Pankaj deep, Manish Gautham | 8 | 18/07/2023 | 100% | Completed | Medium
TASK |  | As a Candidate, I want to be able to build my own resume based on the information, I have provided in my profile, so that I can have a standard ATS friendly resume to apply for jobs.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
TASK |  | As a Candidate, I want to filter the Job Postings on my feed, based on selection criteria including, Skills, Job Title, Location, and Company name, so that I can find Jobs tailored to my preferences.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
TASK | Issue #90 | As a Candidate, I want to be able to view all Job Postings on the Career Services Application, so that I can choose from the various job postings and apply, if I am interested.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
93 | Design wireframe for the Candidate Dashboard | Lakshya Kalia, Sindoora Rao | 8 | 17/07/2023 | 100% | Completed | Medium
94 | Create a Candidate Dashboard in the front end with candidate name, and email, and display all the available job postings as cards with the most recent ones at the top | Lakshya Kalia, Sindoora Rao, Pankaj deep | 13 | 17/07/2023 | 100% | Completed | Medium
95 | Create a GET API to retrieve the Candidate Information from the Candidate Profile table | Pankaj Deep, Manish Gautham | 5 | 17/07/2023 | 100% | Completed | Medium
96 | Create a GET API to retrieve all the records on Job Posting information from the Jobs table | Manish Gautham, Manasa Yalakala | 5 | 17/07/2023 | 100% | Completed | Medium
97 | Schedule the GET API for Job Posting information to autorun every 15 minutes to update newer Jobs | Sadath Roshan, Pankaj Deep | 5 | 17/07/2023 | 100% | Completed | Medium
TASK | Issue #91 | As a Candidate, I want to access individual job postings, so that I can carefully review the Job Details and requirements, and understand the roles and responsibilities clearly, and apply for the same.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
98 | Copy the Wireframe for the Employer job post page, and remove the Candidate list. | Lakshya Kalia, Sindoora Rao | 8 | 18/07/2023 | 100% | Completed | Medium
99 | Create a Job Post page with all the details of the job along with the name of the Employer onto the Database | Sindoora Rao, Manish Gautam, Manasa Yalakala | 13 | 18/07/2023 | 100% | Completed | Medium
100 | Use the GET API to access the Job Posting information | Pankaj Deep, Manish Gautham | 8 | 18/07/2023 | 100% | Completed | Medium
TASK | Issue #92 | As a Candidate, I want to apply for a job, after reviewing the job requirements, in just one click, thereby forwarding my profile to the employer, if I find myself to be a fit for the role, so that I can be a part of the hiring process for the role.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
101 | Create a button "Apply Now" at the end of posting to enable the student to apply for the job | Lakshya Kalia, Sindoora Rao | 5 | 18/07/2023 | 100% | Completed | Medium
102 | Create a popup box to get the Candidate's confirmation to Apply to the job and Notify the candidate that his details will be visible to the employers. | Pankaj Deep, Lakshya Kalia | 3 | 18/07/2023 | 100% | Completed | Medium
103 | Create a popup showing "Application Successful" | Pankaj Deep, Lakshya Kalia | 3 | 18/07/2023 | 100% | Completed | Medium
104 | Use a PUT API to add a new entry with the candidate applying to the job. | Manish Gautam, Pankaj deep | 8 | 18/07/2023 | 100% | Completed | Medium

## SPRINT 3 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 3 BACKLOG | [7 empty] | Completed | High
SPRINT 2 - EPIC 1 - EMPLOYER MANAGEMENT AND JOB POSTING | [5 empty] | % COMPLETED | 12.5% | In Progress | Low
On Hold
TASK | Issue #49 | As an Employer, I want to access each of the applicant's profile page, and also be able to download their Resume's, to help me better review the application, comparing their skills to the job requirments to find the perfect candidate for the postion.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
77 | Create functionality to allow the Employer to download the Candidate's Resume or view it on a separate browser webpage. | Pankaj Deep, Sadath Roshan, Lakshya Kalia | 21 | 18/07/2023 | 25% | In Progress | High
TASK | Issue #51 | As an Employer, I want to be able to shortlist candidates, and find the updated list of candidates, so that I can contact them individually to schedule the next steps of the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
81 | Update the Job Posting Wireframe to add a button at the end of the list to "Shortlist Candidates", which updates the new list to the remaining candidates. | Lakshya Kalia, Sindoora Rao, Manasa Yalakala | 13 | 17/07/2023 | 0% | In Progress | Medium
SPRINT 2 - EPIC 2 - CANDIDATE PROFILE MANAGEMENT AND JOB APPLICATIONS | [5 empty] | % COMPLETED | 0%
TASK | Issue #31 | As a Candidate, I want to create/customize my own profile. I want to be able to provide my Name, Email address, Educational qualifications, Prior work experience (if any), Licences and Certifications, and any relevant skills, I also want to be able to Upload my own resume, so that I can apply to job postings.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
85 | Create UI for the Candidate to enter their Personal Information and update their Professional Experience | Sindoora Rao, Sadath Roshan | 21 | 16/07/2023 | 0% | Not Yet Started | High
86 | Provide option to Upload a file (Resume) in a .pdf or a .docx format on to the profile | Pankaj deep, Sadath Roshan | 13 | 17/07/2023 | 0% | Not Yet Started | Medium
88 | Create a POST API to store the Candidate Profile information using the CandidateID as key | Manish Gautham, Manasa Yalakala | 8 | 18/07/2023 | 0% | Not Yet Started | High
SPRINT 3 - EPIC 3 - TRACKING JOB POSTINGS AND APPLICATIONS | [5 empty] | % COMPLETED | 0%
TASK | Issue #105 | As an Employer, I want to access my dashboard, so that I can track the status of each of the Job post I have created
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
0%
TASK | Issue #106 | As an Employer, I want to be able to view the number of Candidates that have applied for the position on my dashboard without having to open the post itself.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #107 | As an Employer, I want to be notified of any new applications to the Job Post, so that I can review the Candidate's profile at my earliest convenience to smoothen the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #91 | As a Candidate, I want to access individual job postings, so that I can carefully review the Job Details and requirements, and understand the roles and responsibilities clearly, and apply for the same.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #108 | As a Candidate, I want to be able to view the status (Selected, Rejected) of my Job Application, so that I can prepare for the upcoming steps accordingly
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #109 | As a Candidate, I want to be notified of any changes that the employer makes to the job application I have applied to. So I can review the requirements and prepare for the role.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY