## PRODUCT BACKLOG
[10 empty] | STATUS KEY | PRIORITY KEY | TYPE
[10 empty] | Not Yet Started | Medium | User Story
| PRODUCT BACKLOG | [8 empty] | Completed | High | Task
[8 empty] | % COMPLETED | 100% | In Progress | Low | Epic
On Hold
| ISSUE NUMBER | TYPE | USER STORY | ASSIGNEES | STORY POINTS | START DATE | % DONE | STATUS | PRIORITY
| 1 | Task | Setup GitHub to carry out the Project Management Activities of a Scrum Team to track the project workflow | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Medium
| 32 | Task | Complete the Documentation for the SPRINT 1 Deliverables | Manasa Yalakala, Lakshya Kalia | - | 2023-10-07 | 100% | Completed | Medium
| 9 | Epic | EMPLOYER MANAGEMENT AND JOB POSTING |  |  |  |  | % COMPLETED | 100%
| 13 | User Story | As an Employer, I want to be able to create an account on the career services application, so that I can complete the registration process successfully | Pankaj Deep, Manish Gautham, Lakshya Kalia, Sindoora Rao | 13 | 14/07/2023 | 100% | Completed | High
| 20 | User Story | As an Employer, I want to log into my account using my Email and Password, so that I can access the platforms to post jobs and hire candidates | Sadath Roshan, Pankaj Deep, Sindoora Rao, Manasa Yalakala | 8 | 14/07/2023 | 100% | Completed | Medium
| - | User Story | As an Employer, I would like to be able to Update my account information/profile by updating new milestones, or just to keep the profile up-to-date. | Lakshay Kalia, Sadath Roshan, Pankaj Deep, Sindoora Rao | 5 | - | -% | On Hold | Low
| 27 | User Story | As an employer, I want to post job opportunities on the Career Services Application. I would like to post the information on Company Name, Job title, Project/Team name, Job location, Type of work, Expected Start date, Estimated Pay Scale, Job Description, and the Required Skills for the role. So that I can enable candidates to better understand the opportunity they are pursuing. | Team | 21 | 16/07/2023 | 100% | Completed | High
| 47 | User Story | As an Employer, I want to view all of my job postings from my personal dashboard so that I can review each of the posts and make changes if necessary. | Lakshay Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
| 48 | User Story | As an Employer, I want to view individual Job posting and access the list of Candidates who have applied for the position, so that I can review their profile to identify a suitable hire for the role | Lakshay Kalia, Manish Gautham, Pankaj Deep Sahota, Sadath Roshan | 5 | 16/07/2023 | 100% | Completed | High
| 49 | User Story | As an Employer, I want to access each of the applicant's profile page, and also be able to download their Resume's, to help me better review the application, comparing their skills to the job requirmentsto find the perfect candidate for the postion. | Team | 13 | 17/07/2023 | 100% | Completed | Medium
| 50 | User Story | As an Employer, I want the provision to select eligible candidates to move further to the next step of the hiring process or to reject an application that does not meet the requirements. | Lakshay Kalia, Manish Gautham, Pankaj Deep Sahota, Manasa Yalakala | 8 | 17/07/2023 | 100% | Completed | Medium
| 51 | User Story | As an Employer, I want to be able to shortlist candidates, and find the updated list of candidates, so that I can contact them individually to schedule the next steps of the hiring process. | Sindoora Rao, Pankaj Deep Sahota, Manasa Yalakala | 5 | 18/07/2023 | 100% | Completed | Low
| 10 | Epic | CANDIDATE PROFILE MANAGEMENT AND JOB APPLICATION |  |  |  |  | % COMPLETED | 100%
| 14 | User Story | As a Candidate, I want to be able to register on the career services application, so that I can register myself to browse available jobs | Pankaj Deep, Manish Gautham, Lakshya Kalia, Sindoora Rao | 5 | 14/07/2023 | 100% | Completed | High
| 18 | User Story | As a Candidate, I want to log into my account using my Email and Password, so that I can, access the platform's features specific to job seekers. | Sadath Roshan, Pankaj Deep, Sindoora Rao, Manasa Yalakala | 5 | 14/07/2023 | 100% | Completed | Medium
| 31 | User Story | As a Candidate, I want to create/customize my own profile. I want to be able to provide my Name, Email address, Educational qualifications, Prior work experience (if any), Licences and Certifications, and any relevant skills, I also want to be able to Upload my own resume, so that I can apply to job postings. | Team | 34 | 17/07/2023 | 100% | Completed | High
|  | User Story | As a Candidate, I want to be able to build my own resume based on the information, I have provided in my profile, so that I can have a standard ATS friendly resume to apply for jobs. | TBD | - | 18/07/2023 | -% | On Hold | Low
| 90 | User Story | As a Candidate, I want to be able to view all Job Postings on the Career Services Application, so that I can choose from the various job postings and apply, if I am interested. | Manish Gautham, Pankaj Deep, Sadath Roshan, Lakshya Kalia | 8 | 17/07/2023 | 100% | Completed | High
|  | User Story | As a Candidate, I want to filter the Job Postings on my feed, based on selection criteria including, Skills, Job Title, Location, and Company name, so that I can find Jobs tailored to my preferences. | Pankaj Deep, Sadath Roshan, Manasa Yalakala | 13 | 18/07/2023 | 100% | Completed | Medium
0 | 91 | User Story | As a Candidate, I want to access individual job postings, so that I can carefully review the Job Details and requirements, and understand the roles and responsibilities clearly, and apply for the same. | Lakshya Kalia, Pankaj deep, Manish Gautham, Sindoora Rao | 21 | 18/07/2023 | 100% | Completed | High
| 92 | User Story | As a Candidate, I want to apply for a job, after reviewing the job requirements, in just one click, thereby forwarding my profile to the employer, if I find myself to be a fit for the role, so that I can be a part of the hiring process for the role. | Sadath Roshan, Pankaj Deep, Sindoora Rao, Manasa Yalakala | 8 | 18/07/2023 | 100% | Completed | Medium
| 11 | Epic | TRACKING JOB POSTINGS AND APPLICATIONS |  |  |  |  | % COMPLETED | 100%
| 105 | User Story | As an Employer, I want to access my dashboard, so that I can track the status of each of the Job post I have created | Lakshya Kalia, Pankaj deep, Manish Gautham, Sindoora Rao | 8 | 20/07/2023 | 100% | Completed | Medium
| 106 | User Story | As an Employer, I want to be able to view the number of Candidates that have applied for the position on my dashboard without having to open the post itself. | Pankaj Deep, Sadath Roshan, Manasa Yalakala | 13 | 20/07/2023 | 100% | Completed | Medium
| 107 | User Story | As an Employer, I want to be notified of any new applications to the Job Post, so that I can review the Candidate's profile at my earliest convenience to smoothen the hiring process. | Manish Gautham, Pankaj Deep, Sadath Roshan, Lakshya Kalia | 21 | 21/07/2023 | 100% | Completed | Medium
| 108 | User Story | As a Candidate, I want to be able to view the status (Selected, Rejected) of my Job Application, so that I can prepare for the upcoming steps accordingly | Pankaj Deep, Sadath Roshan, Manasa Yalakala | 8 | 20/07/2023 | 100% | Completed | Medium
| 12 | Epic | ADMINISTRATIVE MANAGEMENT OF USER ACCOUNTS, JOB POSTINGS AND APPLICATIONS |  |  |  |  | % COMPLETED | 100%
| 15 | User Story | As an Administrator, I want to be able to login to the career services application, so that I can manage all user profiles | Sadath Roshan, Pankaj Deep, Sindoora Rao, Manasa Yalakala | 5 | 21/07/2023 | 100% | Completed | High
| 134 | User Story | As an Administrator, I want to access the profiles of all users in the application and have the functionality to remove a user. | Lakshya Kalia, Pankaj deep, Manish Gautham, Sindoora Rao | 21 | 21/07/2023 | 100% | Completed | Medium
| 135 | User Story | As an Administrator, I want to be able to access all the Job Posting Information as on the Employer's Dashboard, and view the post insights along with being able to add a new job post or remove an existing one | Sadath Roshan, Pankaj Deep, Sindoora Rao, Manasa Yalakala | 8 | 22/07/2023 | 100% | Completed | Medium
| 136 | User Story | As an Administrator, I want to be able to view individual job posting and see the list of all candidates who have applied for the particular Job Post | Pankaj Deep, Sadath Roshan, Manasa Yalakala | 8 | 23/07/2023 | 100% | Completed | Medium
| 12 | Epic | ADDITIONAL FEATURE -1 : EVENT NOTIFICATIONS |  |  |  |  | % COMPLETED | 100%
| 107 | User Story | As an Employer, I want to be notified of any new applications to the Job Post, so that I can review the Candidate's profile at my earliest convenience to smoothen the hiring process. | Lakshya Kalia, Pankaj deep, Manish Gautham, Sindoora Rao | 13 | 28/07/2023 | 100% | Completed | Medium
| 109 | User Story | As a Candidate, I want to be notified of any changes that the employer makes to the job application I have applied to. So I can review the requirements and prepare for the role. | Sadath Roshan, Pankaj Deep, Sindoora Rao, Manasa Yalakala | 8 | 28/07/2023 | 100% | Completed | Medium
| 156 | User Story | As a Candidate, I want to be able to raise any concerns or issues related to any particular employer or a job posting with the administrator, so that any imposters can be addressed. | Manish Gautham, Pankaj Deep, Sadath Roshan, Lakshya Kalia | 5 | 31/07/2023 | 100% | Completed | Medium
| 107 | User Story | As an Administrator I want to be able to view any concerns raised by the users, and address them appropriately | Sindoora Rao, Pankaj Deep Sahota, Manasa Yalakala | 8 | 31/07/2023 | 100% | Completed | Medium
| 12 | Epic | ADDITIONAL FEATURE - 2 : INSIGHTS |  |  |  |  | % COMPLETED | 100%
| 157 | User Story | As a Candidate, I want to see company insights on number of applicants on particular job postings, so that I can make more informed decisions before applying for a job at a company. | Sindoora Rao, Pankaj Deep Sahota, Manasa Yalakala | 13 | 2023-01-08 | 100% | Completed | Medium
| 158 | User Story | As a Candidate, I want to see insights on various Job Roles posted by a company, so that I can carefully understand the market trend and review my compensation before applying for a role. | Manish Gautham, Pankaj Deep, Sadath Roshan, Lakshya Kalia | - | - | -% | On Hold | Medium