## SPRINT 1 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 1 BACKLOG | [7 empty] | Completed | High
SPRINT 1 - ENVIRONMENT SETUP | [5 empty] | % COMPLETED | 100% | In Progress | Low
On Hold
TASK | Issue #1 | As the Administrator of a Career Services Application, I would like to use GitHub to carry out the Project Management Activities of a Scrum Team to track the project workflow
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
2 | Setup GitHub Repository | Sadath Roshan | - | 2023-07-07 | 100% | Completed | High
3 | Read Documentation on GitHub Projects and watch YouTube videos on setting up Project Board | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Medium
4 | Template the Project Board as a Scrum Project | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Medium
5 | Automate Project Workflows for easier management | Sadath Roshan | - | 2023-07-07 | 100% | Completed | Low
TASK | Issue #32 | Complete the Documentation for the SPRINT 1 Deliverables
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
7 | Document and Update the Minutes of the Product Meeting and the Sprint Planning Meeting | Manasa Yalakala | - | 2023-10-07 | 100% | Completed | High
8 | Update README.md for SPRINT 1 | Lakshya Kalia | - | 2023-10-07 | 100% | Completed | Medium

## SPRINT 2 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 2 BACKLOG | [7 empty] | Completed | High
SPRINT 2 - EPIC 1- EMPLOYER MANAGEMENT AND JOB POSTING | [5 empty] | % COMPLETED | 94.7% | In Progress | Low
On Hold
TASK | Issue #13 | As an Employer, I want to be able to create an account on the career services application, so that I can complete the registration process successfully
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
17 | Create wireframe for the registration screen for employer | Lakshya Kalia | 2 | 14/07/2023 | 100% | Completed | High
21 | Create the registration screen for employer and candidate roles in the frontend | Lakshya Kalia, Sindoora Rao | 5 | 14/07/2023 | 100% | Completed | Medium
52 | Perform Hashing to store the user password for authentication | Pankaj Deep, Sadath Roshan | 8 | 17/07/2023 | 100% | Completed | High
24 | Create the functionality for sending data to backend for registration | Lakshya Kalia, Sindoora Rao, Pankaj Deep, Manasa Yalakala | 5 | 14/07/2023 | 100% | Completed | Medium
53 | Setup the SQL Database and create a table to store the information on - Employers | Pankaj Deep, Sadath Roshan | 8 | 16/07/2023 | 100% | Completed | High
22 | Create a POST API to add employers information to the system database. | Manish Gautam, Pankaj Deep, Manasa Yalakala | 5 | 16/07/2023 | 100% | Completed | Low
TASK | Issue #20 | As an Employer, I want to log into my account using my Email and Password, so that I can access the platforms to post jobs and hire candidates
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
38 | Create wireframe for Login Screen of Employer | Lakshya Kalia, Sindoora Rao | 3 | 16/07/2023 | 100% | Completed | High
39 | Design the Login screen of the Employer | Lakshya Kalia, Sindoora Rao | 5 | 16/07/2023 | 100% | Completed | High
54 | Create the functionality for sending data to backend for login for employer | Manish Gautam, Pankaj Deep, Manasa Yalakala | 5 | 16/07/2023 | 100% | Completed | Medium
44 | Perform User Authentication, by mapping the login password to the hashed password | Pankaj Deep, Sadath Roshan, Manasa Yalakala | 8 | 17/07/2023 | 100% | Completed | Medium
56 | Display Employer dashboard on login | Team | 8 | 16/07/2023 | 100% | Completed | Medium
TASK |  | As an Employer, I would like to be able to Update my account information/profile by updating new milestones, or just to keep the profile up-to-date.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #27 | As an employer, I want to post job opportunities on the Career Services Application. I would like to post the information on Company Name, Job title, Project/Team name, Job location, Type of work, Expected Start date, Estimated Pay Scale, Job Description, and the Required Skills for the role. So that I can enable candidates to better understand the opportunity they are pursuing.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
62 | Create wireframe for forms to enter employer information into the application. | Lakshya Kalia, Manasa Yalakala | 3 | 16/07/2023 | 100% | Completed | Medium
63 | Create wireframe for the Employer Dashboard along with a button to create a new Job Posting. | Lakshya Kalia, Sindoora Rao | 5 | 16/07/2023 | 100% | Completed | Medium
64 | Create confirmation box to display "Job has been posted" once the Employer has successfully submitted the form | Lakshya Kalia, Sindoora Rao | 2 | 16/07/2023 | 100% | Completed | Medium
65 | Create new database table for the Job details to store the Job Posting information with a Job ID | Sadath Roshan, Pankaj Deep | 8 | 16/07/2023 | 100% | Completed | High
66 | Create POST API to create a record of the new jobs in the Jobs tables of the database | Manish Gautham, Pankaj deep | 5 | 17/07/2023 | 100% | Completed | Medium
TASK | Issue #47 | As an Employer, I want to view all of my job postings from my personal dashboard so that I can review each of the posts and make changes if necessary.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
67 | Design UI for the Job Cards with the relevant information | Lakshya Kalia | 5 | 17/07/2023 | 100% | Completed | Medium
68 | Update the Dashboard wireframe with each Job Posting as a card, with Job Title, Job Location, Start Date and a short version of the Job Description is displayed. | Sindoora Rao, Sadath Roshan | 8 | 17/07/2023 | 100% | Completed | Medium
69 | Create a GET API to retrieve all the jobs posted by the Employer using the Employer ID as key from the Jobs table | Manish Gautham, Pankaj deep | 5 | 18/07/2023 | 100% | Completed | High
TASK | Issue #48 | As an Employer, I want to view individual Job posting and access the list of Candidates who have applied for the position, so that I can review their profile to identify a suitable hire for the role
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
70 | Create Wireframe for Job Post page. It should contain the details of the Job Posting, along with a list of all the candidates who have applied for the role. | Lakshya Kalia, Sindoora Rao | 8 | 17/07/2023 | 100% | Completed | Medium
71 | Create the back-end functionality to interface with the database. | Manish Gautham, Manasa Yalakala | 5 | 17/07/2023 | 100% | Completed | Medium
72 | Create GET API to retrieve all the Information of the Job Posting using the Job ID as key | Sadath Roshan, Pankaj deep Sahota | 5 | 17/07/2023 | 100% | Completed | High
73 | Create GET API to retrieve the list of candidates who have applied for the job, using the Candidate ID as key on the Jobs Table | Pankaj Deep, Sadath Roshan, Manish Gautham | 5 | 18/07/2023 | 100% | Completed | High
TASK | Issue #49 | As an Employer, I want to access each of the applicant's profile page, and also be able to download their Resume's, to help me better review the application, comparing their skills to the job requirments to find the perfect candidate for the postion.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
74 | Create each of the candidate names as a clickable field to access the Candidate Profile Page. | Sindoora Rao, Sadath Roshan | 5 | 17/07/2023 | 100% | Completed | Medium
75 | Create a wireframe for the Candidate's Profile Page, containing all the information of the candidate, along with their resume | Lakshya Kalia, Manasa Yalakala | 5 | 18/07/2023 | 100% | Completed | Medium
76 | Create a GET API to retrieve all the Information of the Candidate from their profile, to display to the Employer | Manish Gautham, Pankaj deep | 8 | 18/07/2023 | 100% | Completed | Medium
77 | Create functionality to allow the Employer to download the Candidate's Resume or view it on a separate browser webpage. | Pankaj Deep, Sadath Roshan, Lakshya Kalia | 21 | 18/07/2023 | 25% | In Progress | High
TASK | Issue #50 | As an Employer, I want the provision to select eligible candidates to move further to the next step of the hiring process or to reject an application that does not meet the requirements.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
78 | Update the Candidate Profile wireframe to add two buttons "Select Candidate for Next Round" or "Decline Application" | Sindoora Rao | 8 | 17/07/2023 | 100% | Completed | Medium
79 | Update the Candidate list section of the Job Post Wireframe to highlight the selected candidates in "Green" and provide a button to "Decline Selection" | Lakshya Kalia, Sindoora Rao, Sadath Roshan | 8 | 18/07/2023 | 100% | Completed | Medium
80 | Redirect Employer to the Candidate List once a decision has been made on a Candidate's profile | Sindoora Rao, Manasa Yalakala | 5 | 18/07/2023 | 100% | Completed | Medium
TASK | Issue #51 | As an Employer, I want to be able to shortlist candidates, and find the updated list of candidates, so that I can contact them individually to schedule the next steps of the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
81 | Update the Job Posting Wireframe to add a button at the end of the list to "Shortlist Candidates", which updates the new list to the remaining candidates. | Lakshya Kalia, Sindoora Rao, Manasa Yalakala | 13 | 17/07/2023 | 0% | In Progress | Medium
82 | Create a PUT API to update the status of the Candidate's Application in the Jobs table | Manish Gautham, Pankaj deep | 8 | 18/07/2023 | 100% | Completed | Medium
83 | Create GET API to display a new list of Shortlisted Candidates, with Job ID as key and the application status as Selected from the Jobs table | Sadath Roshan, Pankaj Deep | 8 | 18/07/2023 | 100% | Completed | Medium
SPRINT 2 - EPIC 2 - CANDIDATE PROFILE MANAGEMENT AND JOB APPLICATION | [5 empty] | % COMPLETED | 74.19%
TASK | Issue #14 | As a Candidate, I want to be able to register on the career services application, so that I can register myself to browse available jobs
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
34 | Create a wireframe for Registration screen of Candidate | Lakshya Kalia, Sindoora Rao | 5 | 16/07/2023 | 100% | Completed | Medium
41 | Create a functionality in the backend for registering the Candidate | Lakshya Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
57 | Create a table in the Database to store the Login Information of the Candidates | Manish Gautham, Pankaj deep | 13 | 16/07/2023 | 100% | Completed | High
58 | Create a POST API to register a new Candidate in the database | Manish Gautham, Manasa Yalakala | 8 | 16/07/2023 | 100% | Completed | High
TASK | Issue #18 | As a Candidate, I want to log into my account using my Email and Password, so that I can, access the platform's features specific to job seekers.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
37 | Design a wireframe for the Login page | Lakshya Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
59 | Create a GET API to verify the login credentials of the Candidate | Manish Gautham, Pankaj deep | 8 | 16/07/2023 | 100% | Completed | Medium
60 | Set-up password hashing to ensure that the Candidate's credentials are safely stored and retrieved | Pankaj deep, Sadath Roshan | 13 | 16/07/2023 | 100% | Completed | Medium
61 | Display Candidate Dashboard on Login | Manish Gautham, Manasa Yalakala | 5 | 17/07/2023 | 100% | Completed | High
TASK | Issue #31 | As a Candidate, I want to create/customize my own profile. I want to be able to provide my Name, Email address, Educational qualifications, Prior work experience (if any), Licences and Certifications, and any relevant skills, I also want to be able to Upload my own resume, so that I can apply to job postings.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
84 | Design a wireframe for the Candidate Profile | Lakshya Kalia, Sindoora Rao | 8 | 16/07/2023 | 100% | Completed | Medium
85 | Create UI for the Candidate to enter their Personal Information and update their Professional Experience | Sindoora Rao, Sadath Roshan | 21 | 16/07/2023 | -% | On Hold | High
86 | Provide option to Upload a file (Resume) in a .pdf or a .docx format on to the profile | Pankaj deep, Sadath Roshan | 13 | 17/07/2023 | -% | On Hold | Medium
87 | Create new table in the Database to register the Candidate Profile | Sadath Roshan, Pankaj Deep, Manish Gautham | 8 | 17/07/2023 | 100% | Completed | Medium
88 | Create a POST API to store the Candidate Profile information using the CandidateID as key | Manish Gautham, Manasa Yalakala | 8 | 18/07/2023 | -% | On Hold | High
89 | Create a PUT API to update the Link with the location to the Uploaded Resume file on the Candidate Profile using the candidateID as key | Pankaj deep, Manish Gautham | 8 | 18/07/2023 | 100% | Completed | Medium
TASK |  | As a Candidate, I want to be able to build my own resume based on the information, I have provided in my profile, so that I can have a standard ATS friendly resume to apply for jobs.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
TASK |  | As a Candidate, I want to filter the Job Postings on my feed, based on selection criteria including, Skills, Job Title, Location, and Company name, so that I can find Jobs tailored to my preferences.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
[5 empty] | 0% | Not Yet Started | Medium
TASK | Issue #90 | As a Candidate, I want to be able to view all Job Postings on the Career Services Application, so that I can choose from the various job postings and apply, if I am interested.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
93 | Design wireframe for the Candidate Dashboard | Lakshya Kalia, Sindoora Rao | 8 | 17/07/2023 | 100% | Completed | Medium
94 | Create a Candidate Dashboard in the front end with candidate name, and email, and display all the available job postings as cards with the most recent ones at the top | Lakshya Kalia, Sindoora Rao, Pankaj deep | 13 | 17/07/2023 | 100% | Completed | Medium
95 | Create a GET API to retrieve the Candidate Information from the Candidate Profile table | Pankaj Deep, Manish Gautham | 5 | 17/07/2023 | 100% | Completed | Medium
96 | Create a GET API to retrieve all the records on Job Posting information from the Jobs table | Manish Gautham, Manasa Yalakala | 5 | 17/07/2023 | 100% | Completed | Medium
97 | Schedule the GET API for Job Posting information to autorun every 15 minutes to update newer Jobs | Sadath Roshan, Pankaj Deep | 5 | 17/07/2023 | 100% | Completed | Medium
TASK | Issue #91 | As a Candidate, I want to access individual job postings, so that I can carefully review the Job Details and requirements, and understand the roles and responsibilities clearly, and apply for the same.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
98 | Copy the Wireframe for the Employer job post page, and remove the Candidate list. | Lakshya Kalia, Sindoora Rao | 8 | 18/07/2023 | 100% | Completed | Medium
99 | Create a Job Post page with all the details of the job along with the name of the Employer onto the Database | Sindoora Rao, Manish Gautam, Manasa Yalakala | 13 | 18/07/2023 | 100% | Completed | Medium
100 | Use the GET API to access the Job Posting information | Pankaj Deep, Manish Gautham | 8 | 18/07/2023 | 100% | Completed | Medium
TASK | Issue #92 | As a Candidate, I want to apply for a job, after reviewing the job requirements, in just one click, thereby forwarding my profile to the employer, if I find myself to be a fit for the role, so that I can be a part of the hiring process for the role.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
101 | Create a button "Apply Now" at the end of posting to enable the student to apply for the job | Lakshya Kalia, Sindoora Rao | 5 | 18/07/2023 | 100% | Completed | Medium
102 | Create a popup box to get the Candidate's confirmation to Apply to the job and Notify the candidate that his details will be visible to the employers. | Pankaj Deep, Lakshya Kalia | 3 | 18/07/2023 | 100% | Completed | Medium
103 | Create a popup showing "Application Successful" | Pankaj Deep, Lakshya Kalia | 3 | 18/07/2023 | 100% | Completed | Medium
104 | Use a PUT API to add a new entry with the candidate applying to the job. | Manish Gautam, Pankaj deep | 8 | 18/07/2023 | 100% | Completed | Medium

## SPRINT 3 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 3 BACKLOG | [7 empty] | Completed | High
SPRINT 2 - EPIC 1 - EMPLOYER MANAGEMENT AND JOB POSTING | [5 empty] | % COMPLETED | 100% | In Progress | Low
On Hold
TASK | Issue #49 | As an Employer, I want to access each of the applicant's profile page, and also be able to download their Resume's, to help me better review the application, comparing their skills to the job requirments to find the perfect candidate for the postion.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
77 | Create functionality to allow the Employer to download the Candidate's Resume or view it on a separate browser webpage. | Pankaj Deep, Sadath Roshan, Lakshya Kalia | 21 | 18/07/2023 | 100% | Completed | High
TASK | Issue #51 | As an Employer, I want to be able to shortlist candidates, and find the updated list of candidates, so that I can contact them individually to schedule the next steps of the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
81 | Update the Job Posting Wireframe to add a button at the end of the list to "Shortlist Candidates", which updates the new list to the remaining candidates. | Lakshya Kalia, Sindoora Rao, Manasa Yalakala | 13 | 17/07/2023 | 100% | Completed | Medium
SPRINT 2 - EPIC 2 - CANDIDATE PROFILE MANAGEMENT AND JOB APPLICATIONS | [5 empty] | % COMPLETED | 100%
TASK | Issue #31 | As a Candidate, I want to create/customize my own profile. I want to be able to provide my Name, Email address, Educational qualifications, Prior work experience (if any), Licences and Certifications, and any relevant skills, I also want to be able to Upload my own resume, so that I can apply to job postings.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
85 | Create UI for the Candidate to enter their Personal Information and update their Professional Experience | Sindoora Rao, Sadath Roshan | 21 | 16/07/2023 | 100% | Completed | High
86 | Provide option to Upload a file (Resume) in a .pdf or a .docx format on to the profile | Pankaj deep, Sadath Roshan | 13 | 17/07/2023 | 100% | Completed | Medium
88 | Create a POST API to store the Candidate Profile information using the CandidateID as key | Manish Gautham, Manasa Yalakala | 8 | 18/07/2023 | 100% | Completed | High
SPRINT 3 - EPIC 3 - TRACKING JOB POSTINGS AND APPLICATIONS | [5 empty] | % COMPLETED | 92.5%
TASK | Issue #105 | As an Employer, I want to access my dashboard, so that I can track the status of each of the Job post I have created
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
115 | Create Wireframe for the dashboard so that employers can be able to track the job posts that they have created | Lakshya Kalia, Pankaj Deep | - | 16/07/2023 | 100% | Completed | High
116 | Update the UI for the Employer dashboard to allow the employers to be able to edit the job posting | Sindoora Rao, Manasa Yalakala | 3 | 21/07/2023 | 100% | Completed | Medium
117 | Create a PUT API to update the information in the Job Posting table, which was updated by the employer. | Manish Gautham, Pankaj Deep | 3 | 21/07/2023 | 100% | Completed | Medium
118 | Update the UI to allow the Employer to close the job posting so that no new applications can be allowed | Sadath Roshan, Lakshya Kalia | 2 | 21/07/2023 | 100% | Completed | Medium
119 | Change the Schema of the Job Posting table to add another field 'Active Status' to verify whether the application is still active or the employer has stopped recieving applications | Pankaj Deep, Sadath Roshan | 5 | 21/07/2023 | 100% | Completed | High
TASK | Issue #106 | As an Employer, I want to be able to view the number of Candidates that have applied for the position on my dashboard without having to open the post itself.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
120 | Update the Dashboard wireframe to provide a field for the 'Number of Applicants' in the job cards | Sindoora Rao, Manasa Yalakala | 2 | 22/07/2023 | 75% | In Progress | Medium
121 | Create a POST API to obtain the count of entries in the Jobs tables, and provide it as the number of applicants for a particular job identified using the Jobs ID | Manish Gautham, Pankaj Deep | 3 | 21/07/2023 | 100% | Completed | Medium
122 | Interface the API with the UI to track the outreach of the job posting | Sadath Roshan, Lakshya Kalia | 5 | 21/07/2023 | 100% | Completed | High
TASK | Issue #107 | As an Employer, I want to be notified of any new applications to the Job Post, so that I can review the Candidate's profile at my earliest convenience to smoothen the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #91 | As a Candidate, I want to access individual job postings, so that I can carefully review the Job Details and requirements, and understand the roles and responsibilities clearly, and apply for the same.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
123 | Create a wireframe for the Account Notifications Section | Lakshya Kalia, Sindoora Rao | 13 | 22/07/2023 | 100% | Completed | Medium
124 | Create the interface for the Notifications tab in the frontend | Sindoora Rao, Manish Gautam | 8 | 22/07/2023 | 100% | Completed | Medium
125 | Create a table on the database to host all the notifications including the important fields corresponding to Sender, Reciever, Job ID, etc., | Pankaj Deep, Manish Gautam | 8 | 22/07/2023 | 100% | Completed | Medium
126 | Create a GET API to send notifications to employers when a new entry in the Jobs table is created. | Sadath Roshan, Pankaj Deep | 5 | 22/07/2023 | 50% | In Progress | Medium
127 | Create a wireframe of cards to be added to the notification screen once a new notification is retrieved | Manasa Yalakala, Sindoora Rao | 5 | 22/07/2023 | 100% | Completed | Medium
TASK | Issue #108 | As a Candidate, I want to be able to view the status (Selected, Rejected) of my Job Application, so that I can prepare for the upcoming steps accordingly
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
129 | Create a wireframe for the Candidate, to see each application they have applied to and show the status of the application | Manasa Yalakala, Sindoora Rao | 5 | 22/07/2023 | 100% | Completed | Medium
128 | Design the 'My Application' tab on the Candidate's homepage, on the frontend of the application | Sindoora Rao, Manish Gautam | 8 | 22/07/2023 | 100% | Completed | Medium
130 | Create a GET API to obtain information from the Jobs table on the job posting data based on the Candidate ID in the table | Manish Gautam, Pankaj Deep | 8 | 21/07/2023 | 100% | Completed | Medium
131 | Create a GET API to get the status of the application for a candidate from the jobs table | Pankaj Deep, Sadath Roshan | 3 | 21/07/2023 | 40% | In Progress | Medium
TASK | Issue #109 | As a Candidate, I want to be notified of any changes that the employer makes to the job application I have applied to. So I can review the requirements and prepare for the role.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
132 | Use the UI developed for the Employers notification tab, to provide notification of Job Selections to the Candidates | Manasa Yalakala, Sindoora Rao | 8 | 21/07/2023 | 100% | Completed | Medium
133 | Create a GET API to recieve data from the notifications table based on the Candidate ID | Pankaj Deep, Lakshya Kalia | 5 | 21/07/2023 | 100% | Completed | Medium
SPRINT 3 - EPIC 4 - ADMINISTRATIVE MANAGEMENT OF USER ACCOUNTS, JOB POSTINGS AND APPLICATIONS | [5 empty] | % COMPLETED | 80.36%
TASK | Issue #15 | As an Administrator, I want to be able to login to the career services application, so that I can manage all user profiles
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
26 | Create Wireframe for Login Page for Admin | Lakshya Kalia, Sindoora Rao | - |  | 100% | Completed
28 | Create Login Screen for Admin on the frontend | Manasa Yalakala, Sindoora Rao | 5 | 21/07/2023 | 100% | Completed
25 | Create a Database Table for Admins and create entries for Admin | Pankaj Deep, Manish Gautam | 13 | 21/07/2023 | 100% | Completed
TASK | Issue #134 | As an Administrator, I want to access the profiles of all users in the application and have the functionality to remove a user.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
138 | Create a wireframe for the dashboard for the Administrator, having tabs 'My Account', 'Users', and 'Job Postings' | Manasa Yalakala, Sindoora Rao | 13 | 22/07/2023 | 100% | Completed | High
139 | Create the UI for the dashboard on the frontend of the application | Lakshya Kalia, Sindoora Rao | 21 | 22/07/2023 | 100% | Completed | Medium
140 | Create a wireframe with cards in the dashboard to display all the users, add a drop down menu under the Users section to switch between Employers and Candidates, and for each user, provide an option to remove user | Sadath Roshan, Sindoora Rao, Manish Gautam | 13 | 22/07/2023 | 100% | Completed | High
141 | Create a GET API to retreive the list of all Employers and Candidates from their respective tables onto the dashboard | Pankaj Deep, Manish Gautam | 8 | 23/07/2023 | 25% | In Progress | Medium
142 | Create a PUT API to remove a field from the database in case the Administrator removes a user from the system. | Pankaj Deep, Manish Gautam | 8 | 23/07/2023 | 40% | In Progress | Medium
TASK | Issue #135 | As an Administrator, I want to be able to access all the Job Posting Information as on the Employer's Dashboard, and view the post insights along with being able to add a new job post or remove an existing one
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
143 | Use the UI created for the Employer's dashboard to access information of all job posting | Lakshya Kalia, Sindoora Rao | 5 | 22/07/2023 | 100% | Completed | Medium
144 | Update the UI by adding an option to delete the job posting | Manasa Yalakala, Sindoora Rao | 3 | 23/07/2023 | 100% | Completed | Medium
145 | Create a PUT API to delete the job posting from from the Jobs Table | Pankaj Deep, Manish Gautam | 8 | 23/07/2023 | 25% | In Progress | Medium
TASK | Issue #136 | As an Administrator, I want to be able to view individual job posting and see the list of all candidates who have applied for the particular Job Post
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
146 | Use the UI created for the Employer's dashboard to access information on indvidual job postings and also see the number of candidates applied for the jobs. | Sadath Roshan, Sindoora Rao | 3 | 22/07/2023 | 100% | Completed | Medium
147 | Remove the option to Select or Reject a candidate in the list | Manish Gautam, Manasa Yalakala | 2 | 23/07/2023 | 100% | Completed | Medium
148 | Integrate the UI with the Administrator's role | Pankaj Deep, Sadath Roshan | 5 | 23/07/2023 | 35% | In Progress | Medium

## SPRINT 4 Backlog
| CareerPaths - SOEN 6011 Project | [6 empty] | STATUS KEY | PRIORITY KEY
[8 empty] | Not Yet Started | Medium
SPRINT 4 BACKLOG | [7 empty] | Completed | High
SPRINT 4 ADDITIONAL FEATURE 1 - EVENT NOTIFICATIONS | [5 empty] | % COMPLETED | 100%
TASK | Issue #107 | As an Employer, I want to be notified of any new applications to the Job Post, so that I can review the Candidate's profile at my earliest convenience to smoothen the hiring process.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
TASK | Issue #91 | As a Candidate, I want to access individual job postings, so that I can carefully review the Job Details and requirements, and understand the roles and responsibilities clearly, and apply for the same.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
123 | Create a wireframe for the Account Notifications Section | Lakshya Kalia, Sindoora Rao | 13 | 28/07/2023 | 100% | Completed | Medium
124 | Create the interface for the Notifications tab in the frontend | Sindoora Rao, Manish Gautam | 8 | 31/07/2023 | 100% | Completed | Medium
125 | Create a table on the database to host all the notifications including the important fields corresponding to Sender, Reciever, Job ID, etc., | Pankaj Deep, Manish Gautam | 8 | 28/07/2023 | 100% | Completed | Medium
126 | Create a GET API to send notifications to employers when a new entry in the Jobs table is created. | Sadath Roshan, Pankaj Deep | 5 | 28/07/2023 | 100% | Completed | Medium
127 | Create a wireframe of cards to be added to the notification screen once a new notification is retrieved | Manasa Yalakala, Sindoora Rao | 5 | 31/07/2023 | 100% | Completed | Medium
TASK | Issue #109 | As a Candidate, I want to be notified of any changes that the employer makes to the job application I have applied to. So I can review the requirements and prepare for the role.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
132 | Use the UI developed for the Employers notification tab, to provide notification of Job Selections to the Candidates | Manasa Yalakala, Sindoora Rao | 8 | 28/07/2023 | 100% | Completed | Medium
133 | Create a GET API to recieve data from the notifications table based on the Candidate ID | Pankaj Deep, Lakshya Kalia | 5 | 31/07/2023 | 100% | Completed | Medium
TASK | Issue #155 | As a Candidate, I want to be able to raise any concerns or issues related to any particular employer or a job posting with the administrator, so that any imposters can be addressed.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
164 | Create a wireframe for a Notification Screen | Lakshya Kalia, Sindoora Rao | 8 | 31/07/2023 | 100% | Completed | Medium
165 | Create UI to implement Notification Button and Screen | Lakshya Kalia, Sindoora Rao | 13 | 31/07/2023 | 100% | Completed | Medium
166 | Create API to add new Notifications whenever a Candidate raises a concern, and also take a message as an input. | Manasa Yalakala, Sindoora Rao | 13 | 31/07/2023 | 100% | Completed | Medium
167 | Show a Notification Delivered Popup | Pankaj Deep, Manish Gautam | 8 | 31/07/2023 | 100% | Completed | Low
TASK | Issue #137 | As an Administrator I want to be able to view any concerns raised by the users, and address them appropriately
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
168 | Use the UI developed for the Notification Screen, to provide notification of Concerns from Candidates | Lakshya Kalia, Sindoora Rao | 8 | 31/07/2023 | 100% | Completed | Low
169 | Create a GET API to retreive all the notifications from Candidate addressed to the Admin from the Notifications Table | Pankaj Deep, Manish Gautam | 13 | 31/07/2023 | 100% | Completed | Medium
170 | Use the cards to display the UI of the Notifcations retreived | Sadath Roshan, Pankaj Deep | 8 | 2023-01-08 | 100% | Completed | Medium
SPRINT 4 ADDITIONAL FEATURE 2 - INSIGHTS | [5 empty] | % COMPLETED | 100%
TASK | Issue #157 | As a Candidate, I want to see company insights on number of applicants on particular job postings, so that I can make more informed decisions before applying for a job at a company.
ISSUE NUMBER | STORY TASKS | ASSIGNEES | TASK POINTS | START DATE | % DONE | STATUS | PRIORITY
171 | Create wireframe to display insights on the job posting page | Lakshya Kalia, Sindoora Rao | 13 | 2023-01-08 | 100% | Completed | Medium
172 | Create UI to display the number of applicants applying to the particular job posting | Pankaj Deep, Manish Gautam | 13 | 2023-01-08 | 100% | Completed | Medium
173 | Create GET API to retrieve the number of candidates who have applied to the job posting | Sadath Roshan, Pankaj Deep | 8 | 2023-01-08 | 100% | Completed | Medium